COMMUNITY MARKETPLACE
Development Cost & Financial Projection Report
Irish Market Analysis — 2026

Report Date: 02 July 2026
Prepared from comprehensive codebase audit

# Executive Summary

This report estimates the replacement development cost of the Community Marketplace platform if built from scratch in the Irish market (2026 rates), based on a full audit of the codebase: ~239,000 lines of TypeScript, 67 API controllers, 134+ services, 122+ web routes, ~50 database models, and 20 domain modules.

Estimated development effort: 12,380–18,590 hours (15,485 hours midpoint), equivalent to a team of 5–6 developers over 14–20 months.

Development cost scenarios:

| Scenario | Rate | Low | Mid | High |
| --- | --- | --- | --- | --- |
| Lean Hybrid Team (remote + Irish lead) | €58/hr | €718,040 | €898,130 | €1,078,220 |
| Irish SME Agency / Blended Team | €85/hr | €1,052,300 | €1,316,225 | €1,580,150 |
| Premium Dublin Agency | €125/hr | €1,547,500 | €1,935,625 | €2,323,750 |

The platform significantly exceeds a typical MVP — it includes enterprise-grade RBAC, Stripe Connect payments, real-time chat, fraud detection, monetization SKUs, PDF financial reporting, seller KYC, and a unified admin/super-admin panel with 46+ pages.

# 1. Methodology & Irish Market Benchmarks

## 1.1 Rate Sources (2026)

| Role / Engagement | Rate Range | Source |
| --- | --- | --- |
| Junior freelance developer | €30–€50/hr | Abbacus Technologies, IT Search 2026 |
| Mid-level freelance developer | €50–€80/hr | Abbacus Technologies, IT Search 2026 |
| Senior freelance / specialist | €80–€150/hr | Abbacus Technologies, SalarySavvy Dublin |
| Full-stack contractor (day rate) | €450–€650/day | IT Search Ireland 2026 |
| Irish SME agency (blended) | €85–€120/hr | Industry standard markup on contractor rates |
| Premium Dublin agency | €120–€200/hr | PayMetric Labs, agency benchmarks |
| QA engineer | €45–€65/hr | IT Search Ireland 2026 |
| UX/UI designer | €55–€85/hr | SalarySavvy Dublin 2026 |
| DevOps engineer | €80–€120/hr | SalarySavvy Dublin 2026 |

## 1.2 Estimation Approach

Hours were estimated per feature by auditing actual controllers, services, Prisma models, and frontend components in the monorepo. Each sub-feature reflects implemented code — not planned or placeholder functionality. A 25% contingency is recommended for scope creep, regulatory changes, and integration surprises.

## 1.3 Codebase Metrics

| Metric | Value |
| --- | --- |
| Total TypeScript/TSX lines | ~239,201 |
| API controllers | 67 |
| Domain services | 134+ |
| Frontend routes | 122+ |
| Prisma database models | ~50 |
| API domain modules | 20 |
| Shared Zod schemas | 19 |
| Event listeners | 14 |
| Meilisearch indexes | 4 |
| Documentation files | 89 |
| Default platform transaction fee | 10% |
| Verified seller fee | 8% |
| Monetization SKUs configured | 10 |

# 2. Complete Feature Inventory & Development Costs

Below is every implemented feature and sub-feature, with estimated hours and cost at the Irish SME agency rate (€85/hr). Costs shown are midpoint of low–high hour ranges.

## 1. Foundation & Shared Packages

| Sub-Feature | Hours (Low–High) | Hours (Mid) | Cost @ €85/hr |
| --- | --- | --- | --- |
| Monorepo scaffold (pnpm workspaces) | 40–60 | 50 | €4,250 |
| Shared types package (30+ modules) | 80–120 | 100 | €8,500 |
| Validation package (19 Zod schemas) | 60–90 | 75 | €6,375 |
| Utils, config, brand packages | 50–80 | 65 | €5,525 |
| UI component library | 120–180 | 150 | €12,750 |
| UI dashboard layout & guards | 80–120 | 100 | €8,500 |
| Documentation skeleton (89 docs) | 60–100 | 80 | €6,800 |

Domain subtotal: 490–750 hours | Mid: 620 hrs | Cost: €52,700

## 2. Authentication & Onboarding

| Sub-Feature | Hours (Low–High) | Hours (Mid) | Cost @ €85/hr |
| --- | --- | --- | --- |
| Email/password registration | 40–60 | 50 | €4,250 |
| OTP login (email + phone, 5 purposes) | 80–120 | 100 | €8,500 |
| JWT access + refresh token rotation | 60–90 | 75 | €6,375 |
| Email activation flow + templates | 40–60 | 50 | €4,250 |
| Device fingerprinting & login audit | 30–50 | 40 | €3,400 |
| Pending registration staging | 30–45 | 38 | €3,188 |
| Admin invitation onboarding | 50–80 | 65 | €5,525 |
| Profile completion gate | 20–30 | 25 | €2,125 |
| Account deletion request | 15–25 | 20 | €1,700 |
| Web: login, register, activate pages | 60–90 | 75 | €6,375 |
| Onboarding flow UI | 40–60 | 50 | €4,250 |

Domain subtotal: 465–710 hours | Mid: 588 hrs | Cost: €49,938

## 3. RBAC & User Roles

| Sub-Feature | Hours (Low–High) | Hours (Mid) | Cost @ €85/hr |
| --- | --- | --- | --- |
| 4 system roles (super-admin, admin, seller, buyer) | 40–60 | 50 | €4,250 |
| Custom roles CRUD + templates | 80–120 | 100 | €8,500 |
| Per-user permission overrides (GRANT/DENY) | 60–90 | 75 | €6,375 |
| Scoped RBAC delegation (5 scopes) | 100–150 | 125 | €10,625 |
| Role-based dashboard routing | 30–45 | 38 | €3,188 |
| Seller status lifecycle | 40–60 | 50 | €4,250 |
| Business accounts & ambassador program | 50–75 | 62 | €5,312 |
| Seller limits & custom platform fees | 40–60 | 50 | €4,250 |

Domain subtotal: 440–660 hours | Mid: 550 hrs | Cost: €46,750

## 4. User Profiles & Settings

| Sub-Feature | Hours (Low–High) | Hours (Mid) | Cost @ €85/hr |
| --- | --- | --- | --- |
| Profile CRUD (bio, location, avatar) | 50–75 | 62 | €5,312 |
| R2 presigned upload (avatar, banner) | 60–90 | 75 | €6,375 |
| Phone verification & change OTP | 40–60 | 50 | €4,250 |
| Notification/privacy preferences | 40–60 | 50 | €4,250 |
| Settings pages (buyer/seller/admin) | 80–120 | 100 | €8,500 |

Domain subtotal: 270–405 hours | Mid: 338 hrs | Cost: €28,688

## 5. Listings & Marketplace Core

| Sub-Feature | Hours (Low–High) | Hours (Mid) | Cost @ €85/hr |
| --- | --- | --- | --- |
| Listing CRUD with 11 lifecycle states | 200–300 | 250 | €21,250 |
| Categories tree & community stats | 60–90 | 75 | €6,375 |
| Image upload, confirm, reorder (R2) | 100–150 | 125 | €10,625 |
| Listing packages (FREE, PAID 7/30/60/90D, PREMIUM) | 80–120 | 100 | €8,500 |
| Duplicate, renew, archive, mark sold | 60–90 | 75 | €6,375 |
| Status history & analytics | 50–75 | 62 | €5,312 |
| Admin review thread (seller ↔ admin) | 60–90 | 75 | €6,375 |
| Auto-moderation & fraud triggers | 80–120 | 100 | €8,500 |
| Listing expiry background job | 25–40 | 32 | €2,762 |
| Public browse, search, feeds, nearby areas | 120–180 | 150 | €12,750 |
| Reverse geocode & delivery options | 50–75 | 62 | €5,312 |
| Similar listings & view tracking | 40–60 | 50 | €4,250 |
| Vehicle listing schema & form (1000+ LOC) | 120–180 | 150 | €12,750 |
| Web: listing detail, browse, filters | 200–300 | 250 | €21,250 |
| Web: seller listing form & management | 250–380 | 315 | €26,775 |

Domain subtotal: 1,495–2,250 hours | Mid: 1,872 hrs | Cost: €159,162

## 6. Stores & Storefronts

| Sub-Feature | Hours (Low–High) | Hours (Mid) | Cost @ €85/hr |
| --- | --- | --- | --- |
| Multi-store CRUD & slug management | 80–120 | 100 | €8,500 |
| Store branding (logo, banner, policies) | 60–90 | 75 | €6,375 |
| Opening hours & contact settings | 40–60 | 50 | €4,250 |
| Public store page & listings | 80–120 | 100 | €8,500 |
| Store slot monetization integration | 50–75 | 62 | €5,312 |
| Web: storefront components (15+) | 120–180 | 150 | €12,750 |

Domain subtotal: 430–645 hours | Mid: 538 hrs | Cost: €45,688

## 7. Delivery & Pricing Workflows

| Sub-Feature | Hours (Low–High) | Hours (Mid) | Cost @ €85/hr |
| --- | --- | --- | --- |
| Delivery zones (COLLECTION, LOCAL, NATIONAL, CUSTOM) | 80–120 | 100 | €8,500 |
| Per-listing delivery options | 60–90 | 75 | €6,375 |
| Delivery change review workflow | 80–120 | 100 | €8,500 |
| Pricing preview/update with admin gate | 80–120 | 100 | €8,500 |
| Price change review workflow | 80–120 | 100 | €8,500 |
| Admin delivery & price review pages | 60–90 | 75 | €6,375 |

Domain subtotal: 440–660 hours | Mid: 550 hrs | Cost: €46,750

## 8. Search (Meilisearch)

| Sub-Feature | Hours (Low–High) | Hours (Mid) | Cost @ €85/hr |
| --- | --- | --- | --- |
| 4 indexes (listings, users, categories, chat) | 80–120 | 100 | €8,500 |
| Full-text search with geo-radius filters | 80–120 | 100 | €8,500 |
| Autocomplete & global search | 50–75 | 62 | €5,312 |
| Auto-indexing event listeners | 60–90 | 75 | €6,375 |
| Admin reindex with job status | 40–60 | 50 | €4,250 |
| Search analytics & click tracking | 40–60 | 50 | €4,250 |
| Admin synonyms, stop-words, tuning | 60–90 | 75 | €6,375 |

Domain subtotal: 410–615 hours | Mid: 512 hrs | Cost: €43,562

## 9. Chat & Real-Time Messaging

| Sub-Feature | Hours (Low–High) | Hours (Mid) | Cost @ €85/hr |
| --- | --- | --- | --- |
| Thread CRUD (per listing + buyer + seller) | 80–120 | 100 | €8,500 |
| Message send/edit/delete/read receipts | 80–120 | 100 | €8,500 |
| Socket.IO gateway (typing, presence) | 100–150 | 125 | €10,625 |
| Image attachments (R2 presigned) | 50–75 | 62 | €5,312 |
| Thread archive & blocking | 40–60 | 50 | €4,250 |
| Legacy messages API compatibility | 30–45 | 38 | €3,188 |
| Chat notifications listener | 30–45 | 38 | €3,188 |
| Web: chat window, inbox, modals | 120–180 | 150 | €12,750 |

Domain subtotal: 530–795 hours | Mid: 662 hrs | Cost: €56,312

## 10. Payments & Stripe Connect

| Sub-Feature | Hours (Low–High) | Hours (Mid) | Cost @ €85/hr |
| --- | --- | --- | --- |
| Stripe Connect seller onboarding | 100–150 | 125 | €10,625 |
| PaymentIntent + Checkout Session flows | 120–180 | 150 | €12,750 |
| Platform fee calculation & splits | 60–90 | 75 | €6,375 |
| Webhook handler (idempotent events) | 80–120 | 100 | €8,500 |
| Payment completion & settlement | 80–120 | 100 | €8,500 |
| Buyer purchase history & seller sales | 60–90 | 75 | €6,375 |
| PDF receipt generation + email | 80–120 | 100 | €8,500 |
| Stripe dispute handling | 60–90 | 75 | €6,375 |
| Manual payouts & ledger | 60–90 | 75 | €6,375 |
| Web: buy-now, earnings, payments pages | 150–220 | 185 | €15,725 |

Domain subtotal: 850–1,270 hours | Mid: 1,060 hrs | Cost: €90,100

## 11. Monetization & Buyer Wallet

| Sub-Feature | Hours (Low–High) | Hours (Mid) | Cost @ €85/hr |
| --- | --- | --- | --- |
| Listing boosts (7D/30D) + expiry jobs | 80–120 | 100 | €8,500 |
| Featured homepage/category slots | 80–120 | 100 | €8,500 |
| Fast-track verification purchase | 60–90 | 75 | €6,375 |
| Store slot purchases (2, 3, bundle) | 60–90 | 75 | €6,375 |
| Buyer statement purchase unlock | 60–90 | 75 | €6,375 |
| Cashback grants + cooling period jobs | 80–120 | 100 | €8,500 |
| Buyer wallet & transaction history | 60–90 | 75 | €6,375 |
| Platform purchase invoices (PDF + email) | 60–90 | 75 | €6,375 |
| Admin monetization settings & audit | 60–90 | 75 | €6,375 |
| Web: boost/featured/package dialogs | 100–150 | 125 | €10,625 |

Domain subtotal: 700–1,050 hours | Mid: 875 hrs | Cost: €74,375

## 12. Seller Verification (KYC)

| Sub-Feature | Hours (Low–High) | Hours (Mid) | Cost @ €85/hr |
| --- | --- | --- | --- |
| Multi-step flow (phone, ID, selfie, address) | 150–220 | 185 | €15,725 |
| Document upload & admin review | 80–120 | 100 | €8,500 |
| Fast-track fulfillment integration | 40–60 | 50 | €4,250 |
| Listing gate for unverified sellers | 80–120 | 100 | €8,500 |
| Status history & admin sub-pages | 80–120 | 100 | €8,500 |
| Web: verification flow UI (470+ LOC) | 100–150 | 125 | €10,625 |

Domain subtotal: 530–790 hours | Mid: 660 hrs | Cost: €56,100

## 13. Trust & Reviews

| Sub-Feature | Hours (Low–High) | Hours (Mid) | Cost @ €85/hr |
| --- | --- | --- | --- |
| Buyer reviews seller + pending queue | 60–90 | 75 | €6,375 |
| Seller reviews buyer | 40–60 | 50 | €4,250 |
| Trust profiles (buyer + seller) | 50–75 | 62 | €5,312 |
| Trust cues on listings & storefront | 40–60 | 50 | €4,250 |

Domain subtotal: 190–285 hours | Mid: 238 hrs | Cost: €20,188

## 14. Disputes

| Sub-Feature | Hours (Low–High) | Hours (Mid) | Cost @ €85/hr |
| --- | --- | --- | --- |
| Buyer dispute creation + evidence upload | 80–120 | 100 | €8,500 |
| Dispute timeline & party responses | 60–90 | 75 | €6,375 |
| Admin resolution workflow | 60–90 | 75 | €6,375 |
| Web: buyer/seller/admin dispute pages | 80–120 | 100 | €8,500 |

Domain subtotal: 280–420 hours | Mid: 350 hrs | Cost: €29,750

## 15. Fraud Detection

| Sub-Feature | Hours (Low–High) | Hours (Mid) | Cost @ €85/hr |
| --- | --- | --- | --- |
| 8 signal types + risk scoring | 100–150 | 125 | €10,625 |
| Keyword, location, duplication checks | 80–120 | 100 | €8,500 |
| Event-driven fraud listener | 40–60 | 50 | €4,250 |
| Admin fraud panel + escalation | 60–90 | 75 | €6,375 |

Domain subtotal: 280–420 hours | Mid: 350 hrs | Cost: €29,750

## 16. Moderation

| Sub-Feature | Hours (Low–High) | Hours (Mid) | Cost @ €85/hr |
| --- | --- | --- | --- |
| Report users/listings/messages | 60–90 | 75 | €6,375 |
| Appeals workflow | 50–75 | 62 | €5,312 |
| Action types (warn, suspend, ban, delete) | 80–120 | 100 | €8,500 |
| Content check service | 40–60 | 50 | €4,250 |
| Admin moderation analytics | 60–90 | 75 | €6,375 |
| Chat message moderation | 60–90 | 75 | €6,375 |
| Listing moderation queues | 80–120 | 100 | €8,500 |

Domain subtotal: 430–645 hours | Mid: 538 hrs | Cost: €45,688

## 17. Notifications

| Sub-Feature | Hours (Low–High) | Hours (Mid) | Cost @ €85/hr |
| --- | --- | --- | --- |
| 30+ in-app notification types | 100–150 | 125 | €10,625 |
| FCM push + device registration | 80–120 | 100 | €8,500 |
| Email templates with versioning | 80–120 | 100 | €8,500 |
| Per-channel preferences | 50–75 | 62 | €5,312 |
| Admin broadcast & template CRUD | 80–120 | 100 | €8,500 |
| Provider health & delivery logs | 60–90 | 75 | €6,375 |
| Rate limiting service | 30–45 | 38 | €3,188 |
| Event listeners (14 total across modules) | 100–150 | 125 | €10,625 |

Domain subtotal: 580–870 hours | Mid: 725 hrs | Cost: €61,625

## 18. Admin Panel (46+ pages)

| Sub-Feature | Hours (Low–High) | Hours (Mid) | Cost @ €85/hr |
| --- | --- | --- | --- |
| Dashboard stats & audit log | 80–120 | 100 | €8,500 |
| User management (suspend, ban, verify) | 100–150 | 125 | €10,625 |
| Listing moderation (6 queues) | 120–180 | 150 | €12,750 |
| Seller verification admin (8 sub-pages) | 120–180 | 150 | €12,750 |
| Payments admin (ledger, refunds, disputes) | 100–150 | 125 | €10,625 |
| Finance / platform revenue reports | 80–120 | 100 | €8,500 |
| Search health & reindex admin | 60–90 | 75 | €6,375 |
| Notifications admin | 80–120 | 100 | €8,500 |
| RBAC manager UI (678 LOC) | 100–150 | 125 | €10,625 |
| Admin resource pages (1043 LOC) | 150–220 | 185 | €15,725 |

Domain subtotal: 990–1,480 hours | Mid: 1,235 hrs | Cost: €104,975

## 19. Super-Admin

| Sub-Feature | Hours (Low–High) | Hours (Mid) | Cost @ €85/hr |
| --- | --- | --- | --- |
| Platform settings CRUD | 60–90 | 75 | €6,375 |
| Full RBAC matrix & admin CRUD | 100–150 | 125 | €10,625 |
| Admin invitations system | 80–120 | 100 | €8,500 |
| Operations controller | 60–90 | 75 | €6,375 |
| Super-admin analytics & audit | 60–90 | 75 | €6,375 |

Domain subtotal: 360–540 hours | Mid: 450 hrs | Cost: €38,250

## 20. Finance & Statements

| Sub-Feature | Hours (Low–High) | Hours (Mid) | Cost @ €85/hr |
| --- | --- | --- | --- |
| Buyer account statements (paid unlock) | 100–150 | 125 | €10,625 |
| Seller free monthly statements | 80–120 | 100 | €8,500 |
| Platform revenue report service | 80–120 | 100 | €8,500 |
| PDF layouts (statement, revenue, receipts) | 150–220 | 185 | €15,725 |
| CSV/XLSX export utilities | 60–90 | 75 | €6,375 |
| Web: finance pages & export buttons | 60–90 | 75 | €6,375 |

Domain subtotal: 530–790 hours | Mid: 660 hrs | Cost: €56,100

## 21. Share & Social

| Sub-Feature | Hours (Low–High) | Hours (Mid) | Cost @ €85/hr |
| --- | --- | --- | --- |
| Short link creation & resolution | 40–60 | 50 | €4,250 |
| Share event tracking (8+ channels) | 40–60 | 50 | €4,250 |
| QR code generation | 20–30 | 25 | €2,125 |
| Seller share analytics page | 40–60 | 50 | €4,250 |

Domain subtotal: 140–210 hours | Mid: 175 hrs | Cost: €14,875

## 22. Public Web & PWA

| Sub-Feature | Hours (Low–High) | Hours (Mid) | Cost @ €85/hr |
| --- | --- | --- | --- |
| Homepage (hero, categories, featured) | 80–120 | 100 | €8,500 |
| Static pages (about, help, safety, terms) | 60–90 | 75 | €6,375 |
| Public layout, header, footer, nav | 80–120 | 100 | €8,500 |
| PWA offline fallback | 30–45 | 38 | €3,188 |
| Service worker recovery | 25–40 | 32 | €2,762 |

Domain subtotal: 275–415 hours | Mid: 345 hrs | Cost: €29,325

## 23. Infrastructure & DevOps

| Sub-Feature | Hours (Low–High) | Hours (Mid) | Cost @ €85/hr |
| --- | --- | --- | --- |
| Docker Compose (PostgreSQL, Redis, Meilisearch) | 40–60 | 50 | €4,250 |
| Kubernetes overlays & Traefik TLS | 80–120 | 100 | €8,500 |
| Health checks & Prometheus metrics | 30–45 | 38 | €3,188 |
| Job queue service | 40–60 | 50 | €4,250 |
| R2 cleanup background job | 25–40 | 32 | €2,762 |
| Deploy/rollback/backup runbooks | 60–90 | 75 | €6,375 |
| OVH VPS deployment guide | 30–45 | 38 | €3,188 |

Domain subtotal: 305–460 hours | Mid: 382 hrs | Cost: €32,512

## 24. Security & Compliance

| Sub-Feature | Hours (Low–High) | Hours (Mid) | Cost @ €85/hr |
| --- | --- | --- | --- |
| HTTP exception filter & interceptors | 20–30 | 25 | €2,125 |
| API security patterns & RBAC guards | 60–90 | 75 | €6,375 |
| Stripe webhook signature verification | 20–30 | 25 | €2,125 |
| GDPR-ready data structures | 40–60 | 50 | €4,250 |
| Security checklist documentation | 30–45 | 38 | €3,188 |

Domain subtotal: 170–255 hours | Mid: 212 hrs | Cost: €18,062

## 25. Testing & QA

| Sub-Feature | Hours (Low–High) | Hours (Mid) | Cost @ €85/hr |
| --- | --- | --- | --- |
| Unit & integration test coverage | 400–600 | 500 | €42,500 |
| E2E test scaffolding | 200–300 | 250 | €21,250 |
| Manual QA & UAT cycles | 200–300 | 250 | €21,250 |

Domain subtotal: 800–1,200 hours | Mid: 1,000 hrs | Cost: €85,000

## 2.1 Grand Total — Development Cost

| Scenario | Hours Range | Hours Mid | Base Cost | With 25% Contingency |
| --- | --- | --- | --- | --- |
| Lean Hybrid Team (remote + Irish lead) | 12,380–18,590 | 15,485 | €898,130 | €1,122,662 |
| Irish SME Agency / Blended Team | 12,380–18,590 | 15,485 | €1,316,225 | €1,645,281 |
| Premium Dublin Agency | 12,380–18,590 | 15,485 | €1,935,625 | €2,419,531 |

Recommended budget for full replication in Ireland: €1,645,281 (Irish SME agency, incl. contingency).

# 3. Minimum-Cost Marketing Plan (Irish Market)

This plan prioritises organic growth and grant-funded activities to minimise cash outlay while establishing local presence. Total minimum cash spend: €500/month (€6,000/year) plus founder time investment of ~15 hours/week.

## 3.1 Monthly Budget Breakdown (Minimum Viable)

| Channel / Activity | Monthly Cost | Notes |
| --- | --- | --- |
| Google Business Profile optimisation | €0 | Free — essential for local SEO |
| Organic social media (Instagram, Facebook, TikTok) | €0 | Founder-led content, 5 posts/week |
| Canva Pro (graphics) | €12 | €12.99/mo — listing templates, social assets |
| Mailchimp / Brevo free tier | €0 | Up to 500 contacts, email nurture |
| Buffer free tier (scheduling) | €0 | 3 channels, 10 scheduled posts |
| Google Ads (local intent only) | €250 | €8–10/day — 'buy/sell near me' keywords |
| Facebook/Instagram boost posts | €100 | €25/week on best-performing organic posts |
| Community partnerships & flyers | €50 | Local GAA clubs, community centres |
| Domain + basic SEO tools | €30 | Ubersuggest free + domain renewal amortised |
| Contingency / A/B testing | €58 | Rotate winning ad creative |
| TOTAL MONTHLY | €500 | Minimum viable paid + tool spend |

## 3.2 Free & Grant-Funded Activities

| Programme | Value | Notes |
| --- | --- | --- |
| Trading Online Voucher (LEO) | Up to €2,500 grant | 50% co-funding — website, SEO, ads setup |
| LEO subsidised training | €50–€200 per course | Social media, SEO, digital analytics programmes |
| Local Enterprise Office mentoring | Free | 1:1 business mentor for go-to-market |
| Google Ad Grants (if registered charity) | Up to €8,500/mo | Not applicable unless community NFP structure |
| Referral / ambassador programme | €0 cash | Built into platform — community ambassador feature |
| PR & local media | €0 | Press releases to Irish Times, RTE, local radio |
| SEO content (blog, guides) | €0 | Founder-written 'how to sell safely in Ireland' guides |

## 3.3 Year 1 Marketing Calendar (Minimum Budget)

| Period | Focus |
| --- | --- |
| Month 1–2 | Setup GBP, social profiles, LEO grant application, launch PR |
| Month 3–4 | Start Google Ads (€250/mo), first 10 SEO blog posts, 2 community events |
| Month 5–6 | Referral programme launch, influencer micro-partnerships (product trades) |
| Month 7–8 | Retargeting ads (€100/mo add-on), county-by-county launch posts |
| Month 9–10 | Back-to-school / pre-Christmas seller campaigns |
| Month 11–12 | Holiday peak push, year-in-review content, case studies |

Year 1 total marketing cash cost: €6,000 (€500 × 12) + €1,250 LEO co-funding = effective €7,250 spend for €6,000 out-of-pocket.

# 4. Post-Launch Operating Costs

## 4.1 Monthly Operating Cost Breakdown (Year 1)

| Item | Monthly (€) | Notes |
| --- | --- | --- |
| Cloud hosting (OVH VPS / small K8s) | €250 | API + DB + Redis + Meilisearch |
| Object storage (Cloudflare R2) | €15 | ~50GB images |
| Stripe fees (on platform revenue) | €150 | 1.4% + €0.25 per transaction |
| Email delivery (Resend/SendGrid) | €20 | Up to 50K emails/mo |
| FCM push notifications | €0 | Free tier |
| Domain + SSL | €5 | Amortised |
| Monitoring (Sentry, uptime) | €30 | Developer tier |
| Legal retainer | €290 | €3,500/yr — terms, privacy, consumer rights |
| Accounting / bookkeeping | €125 | €1,500/yr |
| Insurance (cyber + liability) | €165 | €2,000/yr |
| Marketing (minimum plan) | €500 | See Section 3 |
| Part-time community moderator | €1,500 | 20 hrs/mo @ €75/hr |
| Founder salary (deferred/minimum) | €2,000 | Below-market draw |
| Software tools (GitHub, Figma, etc.) | €200 |  |
| TOTAL MONTHLY OPEX | €5,250 | Excl. full dev team |

Annual Year 1 operating cost (excl. new development): €63,000

## 4.2 Weekly & Daily Breakdowns (Year 1 OPEX)

| Period | Operating Cost |
| --- | --- |
| Daily | €172.60 |
| Weekly | €1,211.54 |
| Monthly | €5,250.00 |
| Quarterly | €15,750.00 |
| Annual | €63,000 |

# 5. Revenue Model

Revenue streams implemented in the platform:

| Stream | Price | Description |
| --- | --- | --- |
| Platform transaction fee | 10% default (8% verified sellers) | On in-platform card payments via Stripe Connect |
| Listing boost (7 days) | €1.99 | Increased visibility for 7 days |
| Listing boost (30 days) | €4.99 | Increased visibility for 30 days |
| Featured homepage slot | €2.99/day | 8 slots/day maximum |
| Featured category slot | €1.99/day | 4 slots/day per category |
| Fast-track verification | €2.99 | Priority KYC review |
| Store slot 2 | €4.99 | Additional storefront |
| Store slot 3 | €4.99 | Third storefront |
| Store bundle (3 slots) | €7.99 | Discounted multi-slot |
| Buyer account statement | €0.99 | Monthly PDF/CSV/XLSX unlock |
| Cashback programme | Cost centre | 1.5% cashback — retention tool, not revenue |
| Display advertising (future) | CPM €5–€15 | Not yet implemented — Phase 4+ |

## 5.1 Key Assumptions

| Assumption | Value | Basis |
| --- | --- | --- |
| Average transaction value | €75 | Irish classifieds market average |
| In-platform payment adoption | 25% → 55% | Grows as trust builds (Years 1–10) |
| Platform fee on GMV | 10% | Configurable per seller |
| Seller monetization conversion | 3–8% of active sellers | Boosts, featured, store slots |
| Irish classifieds market | DoneDeal: 6.4M monthly visitors | Distilled Ltd 2024 results |
| Competitor revenue benchmark | €47M (Distilled 2024) | DoneDeal + Daft + Adverts combined |
| Target market share by Year 10 | 0.5–1.5% of addressable | Conservative niche/community positioning |

# 6. Profit & Loss Projection (2026–2035)

Conservative scenario assuming gradual user acquisition competing in the Irish classifieds market. Development cost treated as sunk capital (not amortised into P&L). Stripe costs shown as net platform cost (fees minus pass-through).

| Year | MAU | GMV | Revenue | OpEx | Net P/L | Cumulative P/L |
| --- | --- | --- | --- | --- | --- | --- |
| 2026 | 2,500 | €120,000 | €5,400 | €67,300 | €-61,900 | €-61,900 |
| 2027 | 12,000 | €680,000 | €35,040 | €115,100 | €-80,060 | €-141,960 |
| 2028 | 32,000 | €2,100,000 | €125,100 | €200,000 | €-74,900 | €-216,860 |
| 2029 | 65,000 | €5,200,000 | €336,800 | €334,000 | €2,800 | €-214,060 |
| 2030 | 110,000 | €10,500,000 | €733,500 | €497,000 | €236,500 | €22,440 |
| 2031 | 165,000 | €17,200,000 | €1,253,000 | €676,000 | €577,000 | €599,440 |
| 2032 | 220,000 | €24,800,000 | €1,866,400 | €873,000 | €993,400 | €1,592,840 |
| 2033 | 280,000 | €33,500,000 | €2,571,000 | €1,065,000 | €1,506,000 | €3,098,840 |
| 2034 | 340,000 | €42,000,000 | €3,358,000 | €1,262,000 | €2,096,000 | €5,194,840 |
| 2035 | 400,000 | €51,000,000 | €4,242,000 | €1,470,000 | €2,772,000 | €7,966,840 |

## 6.1 P&L Monthly Breakdown by Year

| Year | Rev/Month | OpEx/Month | Net/Month | Net/Week | Net/Day |
| --- | --- | --- | --- | --- | --- |
| 2026 | €450.00 | €5,608.33 | €-5,158.33 | €-1,190.38 | €-169.59 |
| 2027 | €2,920.00 | €9,591.67 | €-6,671.67 | €-1,539.62 | €-219.34 |
| 2028 | €10,425.00 | €16,666.67 | €-6,241.67 | €-1,440.38 | €-205.21 |
| 2029 | €28,066.67 | €27,833.33 | €233.33 | €53.85 | €7.67 |
| 2030 | €61,125.00 | €41,416.67 | €19,708.33 | €4,548.08 | €647.95 |
| 2031 | €104,416.67 | €56,333.33 | €48,083.33 | €11,096.15 | €1,580.82 |
| 2032 | €155,533.33 | €72,750.00 | €82,783.33 | €19,103.85 | €2,721.64 |
| 2033 | €214,250.00 | €88,750.00 | €125,500.00 | €28,961.54 | €4,126.03 |
| 2034 | €279,833.33 | €105,166.67 | €174,666.67 | €40,307.69 | €5,742.47 |
| 2035 | €353,500.00 | €122,500.00 | €231,000.00 | €53,307.69 | €7,594.52 |

## 6.2 Revenue Breakdown by Source (Annual)

| Year | Transaction Fees | SKU Sales | Advertising | Total Revenue |
| --- | --- | --- | --- | --- |
| 2026 | €3,000 | €2,400 | €0 | €5,400 |
| 2027 | €19,040 | €14,000 | €2,000 | €35,040 |
| 2028 | €65,100 | €48,000 | €12,000 | €125,100 |
| 2029 | €176,800 | €125,000 | €35,000 | €336,800 |
| 2030 | €388,500 | €265,000 | €80,000 | €733,500 |
| 2031 | €688,000 | €420,000 | €145,000 | €1,253,000 |
| 2032 | €1,066,400 | €580,000 | €220,000 | €1,866,400 |
| 2033 | €1,541,000 | €720,000 | €310,000 | €2,571,000 |
| 2034 | €2,058,000 | €880,000 | €420,000 | €3,358,000 |
| 2035 | €2,652,000 | €1,050,000 | €540,000 | €4,242,000 |

## 6.3 Cost Breakdown by Category (Annual)

| Year | Staff | Marketing | Infra+Tools | Stripe | Legal+Other | Total OpEx |
| --- | --- | --- | --- | --- | --- | --- |
| 2026 | €45,000 | €6,000 | €6,000 | €1,800 | €8,500 | €67,300 |
| 2027 | €72,000 | €12,000 | €9,600 | €8,500 | €13,000 | €115,100 |
| 2028 | €110,000 | €28,000 | €18,000 | €22,000 | €22,000 | €200,000 |
| 2029 | €165,000 | €52,000 | €34,000 | €48,000 | €35,000 | €334,000 |
| 2030 | €220,000 | €85,000 | €57,000 | €88,000 | €47,000 | €497,000 |
| 2031 | €280,000 | €120,000 | €78,000 | €138,000 | €60,000 | €676,000 |
| 2032 | €340,000 | €165,000 | €100,000 | €195,000 | €73,000 | €873,000 |
| 2033 | €400,000 | €210,000 | €125,000 | €245,000 | €85,000 | €1,065,000 |
| 2034 | €460,000 | €260,000 | €150,000 | €295,000 | €97,000 | €1,262,000 |
| 2035 | €520,000 | €320,000 | €180,000 | €340,000 | €110,000 | €1,470,000 |

Projected break-even year: 2029 (operating profit positive). Cumulative cash burn to break-even: estimated €0–€7,966,840 depending on growth trajectory.

# 7. Five-Year Summary (2026–2030)

| Year | Revenue | OpEx | Net P/L | Rev/Month | Net/Month |
| --- | --- | --- | --- | --- | --- |
| 2026 | €5,400 | €67,300 | €-61,900 | €450.00 | €-5,158.33 |
| 2027 | €35,040 | €115,100 | €-80,060 | €2,920.00 | €-6,671.67 |
| 2028 | €125,100 | €200,000 | €-74,900 | €10,425.00 | €-6,241.67 |
| 2029 | €336,800 | €334,000 | €2,800 | €28,066.67 | €233.33 |
| 2030 | €733,500 | €497,000 | €236,500 | €61,125.00 | €19,708.33 |

# 8. Future Development Roadmap & Costs

Based on docs/product/roadmap.md and competitive gap analysis vs DoneDeal/Adverts.ie.

| Initiative | Description | Target | Hours | Cost @ €85/hr |
| --- | --- | --- | --- | --- |
| Phase 4 — Multi-tenancy | Community/neighborhood scopes, white-label | Q2 2027 | 1,200–1,800 | €127,500 |
| Native mobile apps (iOS + Android) | React Native or Flutter apps | Q3 2027 | 2,400–3,600 | €255,000 |
| Advanced analytics dashboard | Seller insights, cohort analysis, funnels | Q4 2027 | 600–900 | €63,750 |
| GDPR data export & deletion tooling | Automated compliance workflows | Q1 2028 | 400–600 | €42,500 |
| Public API & partner webhooks | Third-party integrations SDK | Q2 2028 | 800–1,200 | €85,000 |
| AI listing descriptions & moderation | LLM-assisted content generation/review | Q3 2028 | 600–1,000 | €68,000 |
| Escrow & buyer protection fund | Held funds until delivery confirmed | Q4 2028 | 1,000–1,500 | €106,250 |
| Shipping integrations (An Post, DPD) | Label generation & tracking | Q1 2029 | 800–1,200 | €85,000 |
| Auction/bidding system | Timed auctions for high-value items | Q2 2029 | 1,000–1,500 | €106,250 |
| B2B dealer portal | Bulk listings, inventory sync, CRM | Q3 2029 | 1,500–2,200 | €157,250 |
| International expansion (UK) | Multi-currency, cross-border compliance | Q4 2029 | 2,000–3,000 | €212,500 |
| Video listings & live selling | Short-form video, live stream commerce | 2029–2030 | 1,800–2,600 | €187,000 |

Total future development (Phases 4–6): 14,100–21,100 hours | Estimated cost: €1,496,000 (excl. contingency)

# 9. Development Cost — Time-Based Breakdowns

Assuming 18-month build timeline at midpoint cost of €1,316,225:

| Metric | Value |
| --- | --- |
| Total project cost | €1,316,225 |
| Monthly burn (dev only) | €73,123.61 |
| Weekly burn (dev only) | €16,887.67 |
| Daily burn (dev only, 5-day week) | €3,323.80 |
| Hourly burn (mid hours) | €85.00 |
| Team size equivalent | 5–6 FTE developers |
| Calendar timeline | 14–20 months |

# 10. Risk Factors & Sensitivities

| Risk | Severity | Mitigation |
| --- | --- | --- |
| Market dominance of DoneDeal/Adverts.ie | High | Differentiate on community, zero-fee listings, trust |
| Slow in-platform payment adoption | High | Buyer protection incentives, cashback programme |
| Regulatory (PSD2, consumer rights) | Medium | Legal review, Stripe handles most compliance |
| Development cost overrun | Medium | 25% contingency recommended; phased delivery |
| Key person dependency | Medium | Document architecture; hire second senior dev early |
| Cybersecurity incident | Medium | Cyber insurance, penetration testing (€5–15K) |
| Currency/tax changes post-Brexit | Low | EUR-only operations; Irish Ltd structure |

# Appendix A: Irish Market Context

| Benchmark | Value | Source |
| --- | --- | --- |
| DoneDeal monthly visitors | 6.4 million | Distilled Ltd 2024 |
| Adverts.ie monthly users | ~2 million | Distilled Ltd 2024 |
| Adverts.ie new listings/month | 200,000+ | Distilled Ltd 2024 |
| Distilled Ltd revenue (2024) | €47 million | RTE / filed accounts |
| Distilled Ltd pre-tax profit (2024) | €7.55 million | Down 38% YoY |
| Typical Irish agency project (marketplace) | €500K–€2M | Industry benchmarks |
| LEO Trading Online Voucher | Up to €2,500 | 50% co-funded |
| Minimum viable marketing (Ireland) | €500–€1,000/mo | ProfileTree, BeFound 2026 |

# Appendix B: Default Platform Pricing (from codebase)

| SKU / Setting | Default Price |
| --- | --- |
| boost_7d | €1.99 |
| boost_30d | €4.99 |
| featured_homepage | €2.99 |
| featured_category | €1.99 |
| fast_track_verification | €2.99 |
| store_slot_2 | €4.99 |
| store_slot_3 | €4.99 |
| store_bundle_3 | €7.99 |
| buyer_statement | €0.99 |
| platform_fee_default | 10% |
| verified_seller_fee | 8% |
| cashback | 1.5% |

# Appendix C: Glossary of Abbreviations

All abbreviations and acronyms used in this report, grouped by category.

## Financial & Business Terms

| Abbreviation | Full meaning & context in this report |
| --- | --- |
| MAU | Monthly Active Users — unique users who visit or use the platform at least once in a calendar month. Key growth metric. |
| GMV | Gross Merchandise Value — total euro value of all goods/services sold through the platform in a period, before fees and refunds. |
| OpEx | Operating Expenses — day-to-day running costs (staff, hosting, marketing, legal, tools) excluding one-off capital spend. |
| P&L / P/L | Profit and Loss — financial statement showing revenue minus costs; net result is profit or loss. |
| SKU | Stock Keeping Unit — a distinct paid product or service (e.g. 7-day listing boost, featured slot). Each SKU has its own price. |
| CPM | Cost Per Mille — advertising cost per 1,000 impressions (views) of an ad. |
| SME | Small and Medium Enterprise — Irish/EU classification for businesses below large-corporate size; used for agency and grant context. |
| MVP | Minimum Viable Product — smallest feature set needed to launch and test with real users. |
| FTE | Full-Time Equivalent — one person working full-time; e.g. '5–6 FTE' means a team of five to six full-time developers. |
| YoY | Year over Year — comparison of a metric in one year vs the same period in the previous year. |
| B2B | Business to Business — selling tools or services to other businesses (e.g. dealer portal) rather than consumers. |
| CRM | Customer Relationship Management — software for managing customer/dealer contacts and sales pipelines. |
| Ltd | Limited — Irish/UK private company structure (e.g. Distilled Ltd); shareholders' liability is limited to their investment. |
| NFP | Not-for-Profit — organisation structure that may qualify for schemes like Google Ad Grants. |
| PSD2 | Payment Services Directive 2 — EU regulation governing electronic payments, strong customer authentication, and open banking. |

## Revenue & Cost Line Items

| Abbreviation | Full meaning & context in this report |
| --- | --- |
| Transaction fee revenue | Platform's cut (default 10%) on sales paid through in-platform Stripe payments. |
| SKU revenue | Income from sellers/buyers purchasing paid add-ons (boosts, featured slots, verification fast-track, etc.). |
| Stripe cost | Payment processing fees charged by Stripe (typically ~1.4% + €0.25 per card transaction in Ireland). |
| Infra + Tools | Infrastructure (servers, storage) plus software subscriptions (monitoring, email, GitHub, etc.). |
| Cumulative P/L | Running total of net profit/loss from launch year through each projection year. |
| Break-even | Point where annual revenue equals or exceeds operating expenses (operating profit ≥ 0). |
| Contingency | Extra budget buffer (report uses 25%) for scope creep, delays, and unknowns. |

## Marketing & Irish Programmes

| Abbreviation | Full meaning & context in this report |
| --- | --- |
| LEO | Local Enterprise Office — Irish government network offering grants, mentoring, and training to small businesses in every county. |
| Trading Online Voucher | LEO grant of up to €2,500 (50% matched by you) for e-commerce, website, SEO, and digital marketing. |
| GBP | Google Business Profile — free Google listing for local search and maps visibility (formerly Google My Business). |
| SEO | Search Engine Optimisation — improving organic (unpaid) ranking in Google and other search engines. |
| PR | Public Relations — media outreach, press releases, and coverage in newspapers, radio, and online. |
| GAA | Gaelic Athletic Association — Ireland's largest community sports body; useful for local partnership marketing. |
| RTE | Raidió Teilifís Éireann — Ireland's national public broadcaster (TV and radio). |
| mo | Per month — e.g. €500/mo = €500 per month. |
| hr / hrs | Hour(s) — used for developer rates and time estimates. |

## Technology — Platform & Architecture

| Abbreviation | Full meaning & context in this report |
| --- | --- |
| API | Application Programming Interface — backend endpoints the web and mobile apps call to read/write data. |
| REST | Representational State Transfer — standard style for HTTP APIs (GET, POST, PATCH, DELETE). |
| JWT | JSON Web Token — secure token format for login sessions and API authentication. |
| OTP | One-Time Password — short code sent by email or SMS for login, registration, or verification. |
| RBAC | Role-Based Access Control — permissions tied to roles (buyer, seller, admin) rather than hard-coded per user. |
| KYC | Know Your Customer — identity verification process (ID, selfie, address) for sellers. |
| CRUD | Create, Read, Update, Delete — basic data operations for any entity (listings, users, etc.). |
| SDK | Software Development Kit — packaged tools for third parties to integrate with your platform. |
| Webhook | Automated HTTP callback — e.g. Stripe notifying your server when a payment succeeds. |

## Technology — Frontend & UX

| Abbreviation | Full meaning & context in this report |
| --- | --- |
| UI | User Interface — visual elements users interact with (buttons, forms, tables). |
| UX | User Experience — overall ease and quality of using the product. |
| PWA | Progressive Web App — website that can work offline and be installed like an app on phones. |
| TS / TSX | TypeScript / TypeScript + JSX — programming languages used across this codebase. |
| LOC | Lines of Code — rough measure of codebase size (~239,000 in this project). |

## Technology — Infrastructure & Services

| Abbreviation | Full meaning & context in this report |
| --- | --- |
| DevOps | Development Operations — practices and tooling for deploying, monitoring, and scaling software. |
| VPS | Virtual Private Server — rented cloud server (e.g. OVH) hosting the API and databases. |
| K8s | Kubernetes — container orchestration for scaling multiple services in production. |
| TLS | Transport Layer Security — encryption for HTTPS (padlock in the browser). |
| R2 | Cloudflare R2 — object storage for images and files (similar to AWS S3). |
| FCM | Firebase Cloud Messaging — Google's push notification service for mobile and web. |
| CDN | Content Delivery Network — geographically distributed cache for faster image and static file delivery. |
| HPA | Horizontal Pod Autoscaler — Kubernetes feature that adds/removes server instances based on load. |
| OVH | French cloud/hosting provider commonly used for EU-based VPS deployments. |

## Technology — Data & Documents

| Abbreviation | Full meaning & context in this report |
| --- | --- |
| PDF | Portable Document Format — downloadable receipts, statements, and revenue reports. |
| CSV | Comma-Separated Values — spreadsheet-friendly export format for financial data. |
| XLSX | Microsoft Excel Open XML — Excel workbook format for statement and report exports. |
| GDPR | General Data Protection Regulation — EU privacy law governing personal data collection and user rights. |

## Technology — Testing & Quality

| Abbreviation | Full meaning & context in this report |
| --- | --- |
| QA | Quality Assurance — systematic testing to find bugs before release. |
| UAT | User Acceptance Testing — final testing with real or representative users before go-live. |
| E2E | End-to-End — automated tests that simulate a full user journey through the app. |

## Technology — AI & Future Features

| Abbreviation | Full meaning & context in this report |
| --- | --- |
| LLM | Large Language Model — AI systems (e.g. GPT) used for auto-generating listing text or moderation assist. |
| AI/ML | Artificial Intelligence / Machine Learning. |

## Vehicle Listings (Irish Context)

| Abbreviation | Full meaning & context in this report |
| --- | --- |
| NCT | National Car Test — Ireland's mandatory periodic vehicle roadworthiness certificate. |
| VIN | Vehicle Identification Number — unique 17-character ID for every motor vehicle. |

## Payment & Compliance

| Abbreviation | Full meaning & context in this report |
| --- | --- |
| Stripe Connect | Stripe's marketplace product — splits payments between platform and sellers, handles payouts. |
| PaymentIntent | Stripe object representing a single card payment attempt. |
| Express dashboard | Stripe-hosted portal where sellers view payouts and tax documents. |

## Time & Project Planning

| Abbreviation | Full meaning & context in this report |
| --- | --- |
| Q1–Q4 | Calendar quarters — Q1 = Jan–Mar, Q2 = Apr–Jun, Q3 = Jul–Sep, Q4 = Oct–Dec. |
| Mid | Midpoint estimate — average of low and high range in hour/cost tables. |
| Low / High | Optimistic vs pessimistic bounds on hours or cost estimates. |

# Appendix D: Disclaimer

This report provides indicative estimates based on codebase analysis and publicly available Irish market rate data (2026). Actual costs depend on team composition, delivery model, scope changes, and market conditions. P&L projections are conservative models — not financial advice. Revenue assumptions should be validated with market research and pilot launch data. Development hours reflect replacement cost of existing implemented features, not ongoing maintenance (estimated at 15–20% of build cost annually).